## Start Here
section | value
Purpose | One cohesive workbook with a sequenced software build-up and manual fill sheets for mechanical, electronics, and manufacturing streams
How to use | Drive execution from the Software Sequence sheet. Fill Mechanical, Electronics, and Manufacturing from the Manual Streams sheet by hand.
Reality link | Use Repo Artifacts, Snapshot, and Module Health as the live project mirror sourced from TerrestraX and ArchEx.
Generated at | 2026-04-22T08:07:04.327013+00:00

## Software Sequence
step_id | sequence | title | objective | entry_criteria | done_criteria | primary_anchor | supporting_anchor | validation | depends_on
SW-01 | 1 | Refresh architecture baseline | Keep architecture.md and ArchEx outputs current so code structure and next steps stay grounded in reality | The repo builds enough for ArchEx to analyze it | architecture.md, .archex/metrics.json, and .archex/graph.json reflect the current codebase | architecture.md | .archex/metrics.json | ArchEx regenerate completes and outputs are reviewed
SW-02 | 2 | Validate single-leg kinematics and IK | Prove one leg can reach commanded targets repeatably before broadening to full-body behavior | Nominal geometry and a single-leg controller scenario are available | Single-leg controller hits targets within agreed tolerance in simulation | core/inverse_kinematics.py | controllers/spider_static_controller/static_leg_common.py | Simulation run with target error acceptance bounds | SW-01
SW-03 | 3 | Implement raise-to-nominal posture | Move safely from motor zero to the working posture you want to operate from | Motor-zero and nominal posture definitions both exist | Controller state machine can transition from q=[0,0,0] to nominal without unsafe transient motion | robots/rconfig.py | controllers/spider_static_controller | Simulation scenario confirms bounded transition to nominal | SW-02
SW-04 | 4 | Separate trajectory paths from time laws | Make locomotion composable by cleanly separating spatial paths from temporal scheduling | Current locomotion update path is understood and stable enough to refactor | Locomotion couples reusable path and time-law functions instead of hardcoding both inline | core/locomotion/locomotion.py | core/trajectory | Code review plus focused simulation check of the refactored gait path | SW-03
SW-05 | 5 | Integrate full gait generation in simulation | Produce stable per-leg targets and phase behavior across the whole robot in Webots | Reusable locomotion, IK, and nominal posture pieces are available | A chosen world demonstrates stable commanded stepping behavior in simulation | worlds | core/locomotion/locomotion.py | World-specific simulation evidence for nominal stance and motion | SW-04
SW-06 | 6 | Connect operator input and motion states | Let the console or joystick trigger posture transitions and teleop motion in a controlled state machine | Input wrapper and gait controller entry points are available | Operator commands can raise to nominal and then drive movement through explicit states | controllers/connectors/webots_joystick.py | controllers | Input integration test confirms correct state transitions | SW-05
SW-07 | 7 | Prepare hardware-facing bring-up | Align the software stack with calibration, interface, and safety expectations needed for real hardware | Simulation posture and motion control are stable enough to inform hardware integration | Bring-up sequence, interface assumptions, and validation gates are explicit | controllers/connectors | robots/rconfig.py | Bring-up checklist and validation matrix are complete and reviewed | SW-06

## Manual Streams
stream_id | name | focus | status | owner | next_step | blocking_risk | evidence_link | prompt_1 | prompt_2 | prompt_3
MAN-MECH | Mechanical | Geometry, CAD, assembly, tolerances, linkage fit, body packaging | manual |  |  |  |  | What is the next physical design decision that blocks software or integration? | What evidence proves this mechanical step is done? | Which repo or external artifact should this row point to?
MAN-ELEC | Electronics | Power, motor interfaces, buses, wiring, controller boards, protections | manual |  |  |  |  | What interface or power constraint is currently limiting integration? | What bench test or schematic evidence closes this item? | Which document, diagram, or note should this row reference?
MAN-MFG | Manufacturing and Procurement | Bought parts, fabricated parts, assembly readiness, sourcing risk | manual |  |  |  |  | Which part or fabrication step is next on the critical path? | What status tells you it is no longer a blocker? | What vendor, drawing, or BOM line should be linked here?

## Mechanical
item_id | stream | focus_area | status | owner | next_step | blocking_risk | evidence_link | prompt_1 | prompt_2 | prompt_3 | notes
MAN-MECH-001 | Mechanical | Geometry, CAD, assembly, tolerances, linkage fit, body packaging | not-started |  |  |  |  | What is the next physical design decision that blocks software or integration? | What evidence proves this mechanical step is done? | Which repo or external artifact should this row point to?

## Electronics
item_id | stream | focus_area | status | owner | next_step | blocking_risk | evidence_link | prompt_1 | prompt_2 | prompt_3 | notes
MAN-ELEC-001 | Electronics | Power, motor interfaces, buses, wiring, controller boards, protections | not-started |  |  |  |  | What interface or power constraint is currently limiting integration? | What bench test or schematic evidence closes this item? | Which document, diagram, or note should this row reference?

## Manufacturing
item_id | stream | focus_area | status | owner | next_step | blocking_risk | evidence_link | prompt_1 | prompt_2 | prompt_3 | notes
MAN-MFG-001 | Manufacturing and Procurement | Bought parts, fabricated parts, assembly readiness, sourcing risk | not-started |  |  |  |  | Which part or fabrication step is next on the critical path? | What status tells you it is no longer a blocker? | What vendor, drawing, or BOM line should be linked here?

## Validation
validation_id | linked_item_id | discipline | validation_type | target_artifact | scenario_or_world | acceptance_criteria | evidence_location | status | owner | notes
VAL-001 | TTX-002 | simulation | simulation | core/inverse_kinematics.py | worlds/spider_static_test.wbt | Leg target error stays within agreed tolerance |  | not-started
VAL-002 | TTX-003 | integration | simulation | robots/rconfig.py | worlds/spider_static_test.wbt | Robot reaches nominal posture without unsafe transient motion |  | not-started
VAL-003 | TTX-004 | software | code-review | core/locomotion/locomotion.py |  | Path generation and time-law coupling are separated cleanly |  | not-started
VAL-004 | TTX-005 | integration | simulation | controllers/connectors/webots_joystick.py | worlds/spider_world.wbt | Raise and motion commands are recognized and routed correctly |  | not-started
VAL-005 | TTX-006 | electronics | bench-test | controllers/connectors |  | Interface signals and constraints are documented and checked |  | not-started

## Risks
risk_id | title | category | severity | likelihood | status | owner | linked_item_id | trigger | mitigation | next_review | notes
RISK-001 | Architecture baseline becomes stale | software | medium | medium | open |  | TTX-001 | Code structure changes without ArchEx refresh | Refresh architecture outputs when structure changes
RISK-002 | Nominal posture transition causes unsafe transient | controls | high | medium | open |  | TTX-003 | Raise-to-nominal sequence is commanded without bounded transition | Use controlled interpolation and simulation validation before hardware
RISK-003 | Simulation behavior diverges from hardware | systems | high | medium | open |  | TTX-004 | Trajectory assumptions are only tested in simulation | Define explicit simulation-to-hardware validation gates
RISK-004 | Electronics documentation stays fragmented | electronics | medium | high | open |  | TTX-006 | Wiring and interfaces live in ad hoc notes | Create a single interface inventory and update it with each integration change

## BOM
bom_id | part_name | discipline | category | qty | unit | status | source_or_vendor | linked_workstream | linked_milestone | owner | notes
BOM-001 | Spider chassis frame | mechanical | fabricated | 1 | assembly | unknown |  | WS-MECH | M6
BOM-002 | Leg linkage set | mechanical | fabricated | 4 | set | unknown |  | WS-MECH | M6
BOM-003 | Servo or motor set | electronics | bought | 12 | unit | unknown |  | WS-ELEC | M6
BOM-004 | Motor driver or controller board | electronics | bought | 1 | unit | unknown |  | WS-ELEC | M6
BOM-005 | Power supply subsystem | electronics | bought | 1 | assembly | unknown |  | WS-ELEC | M6

## Repo Artifacts
artifact_id | name | discipline | path | kind | exists | purpose
ARCHITECTURE | Architecture Reference | software | architecture.md | file | TRUE | ArchEx-generated architecture baseline and module contracts
ARCH_EX_METRICS | ArchEx Metrics | software | .archex/metrics.json | file | TRUE | Module health metrics for coupling and cohesion
ARCH_EX_GRAPH | ArchEx Graph | software | .archex/graph.json | file | TRUE | Dependency graph for modules and symbols
ROBOT_CONFIG | Robot Config Guide | mechanical | SPIDER_ROBOT_CONFIG.md | file | TRUE | Geometry and standing-pose reference
CONTROLLERS | Controllers | software | controllers | directory | TRUE | Runtime control entry points and hardware/sim connectors
CORE | Core Motion Stack | software | core | directory | TRUE | IK, kinematics, locomotion, and trajectory modules
ROBOTS | Robot Configuration | software | robots | directory | TRUE | Robot model configuration and nominal-pose helpers
WORLDS | Simulation Worlds | simulation | worlds | directory | TRUE | Webots scenarios used for simulation validation
PROTOS | Webots Protos | simulation | protos | directory | TRUE | Robot and world object definitions
CI_PIPELINE | CI Pipeline | software | .github/workflows/ci.yml | file | TRUE | Automation hook for lint, smoke checks, and future tracker refresh

## Module Health
module_id | file | ca | ce | total_coupling | lcom4 | cohesion_rating | components | symbol_count
controllers.connectors.hud | controllers/connectors/hud.py | 2 | 0 | 2 | 10 | low | 10 | 14
controllers.connectors.webots_joystick | controllers/connectors/webots_joystick.py | 1 | 0 | 1 | 17 | low | 17 | 27
controllers.gamepad_debug_controller.gamepad_debug_controller | controllers/gamepad_debug_controller/gamepad_debug_controller.py | 0 | 4 | 4 | 2 | medium | 2 | 2
controllers.spider_static.spider_core | controllers/spider_static/spider_core.h | 0 | 2 | 2 | 1 | high | 1 | 1
controllers.spider_static_controller.spider_static_controller | controllers/spider_static_controller/spider_static_controller.py | 0 | 3 | 3 | 12 | low | 12 | 12
controllers.spider_static_test_rev01_mk01.spider_static_test_rev01_mk01 | controllers/spider_static_test_rev01_mk01/spider_static_test_rev01_mk01.py | 0 | 1 | 1 | 4 | low | 4 | 4
core.dtypes | core/dtypes.py | 5 | 0 | 5 | 21 | low | 21 | 21
core.kinematics | core/kinematics.py | 0 | 0 | 0 | 2 | medium | 2 | 5
core.kinematics_rev01 | core/kinematics_rev01.py | 0 | 0 | 0 | 1 | high | 1 | 3
core.kinematics_symbolic_rev02 | core/kinematics_symbolic_rev02.py | 0 | 1 | 1 | 1 | high | 1 | 9
core.pose | core/pose.py | 0 | 1 | 1 | 5 | low | 5 | 5
core.trajectory | core/trajectory.py | 0 | 0 | 0 | 1 | high | 1 | 0
robots.config_rev01 | robots/config_rev01.py | 0 | 1 | 1 | 1 | high | 1 | 1
robots.config_temp | robots/config_temp.py | 0 | 1 | 1 | 10 | low | 10 | 10
robots.model | robots/model.py | 0 | 0 | 0 | 1 | high | 1 | 0
robots.rconfig | robots/rconfig.py | 0 | 1 | 1 | 1 | high | 1 | 1

## Snapshot
metric | value
generated_at_utc | 2026-04-22T08:07:04.339936+00:00
artifact_count | 10
workstream_count | 8
milestone_count | 8
top_level_directory_count | 10
python_file_count | 30
world_file_count | 11
proto_file_count | 2
architecture_md_present | TRUE
archex_metrics_present | TRUE
archex_graph_present | TRUE
ci_pipeline_present | TRUE